## Executive Summary
Executive Summary
Website modernization tracker organized by planned delivery month.
Total Websites |  | Live |  | In Progress |  | To Be Revamped |  | Completion
28 |  | 10 |  | 1 |  | 17 |  | 35.71%
Navigation |  |  | Next Scheduled Deliveries
Open organized website tracker |  |  | Order | Institution | Status | Launch | Go to Row
Open Gantt view |  |  | 11 | Apeejay School, Sheikh Sarai | WIP | Mar 2026 | Open
|  |  | 12 | Apeejay School, Nerul | TBR | Apr 2026 | Open
|  |  | 13 | Apeejay School, Khargar | TBR | May 2026 | Open
|  |  | 14 | Apeejay School, Mahavir Marg | TBR | May 2026 | Open
|  |  | 15 | Apeejay School, Rama Mandi, Hoshiarpur | TBR | May 2026 | Open
Status Mix
Live | 10
WIP | 1
TBR | 17

## Website Tracker
Website Tracker
Rows are organized by chronological delivery / launch month.
Back to Executive Summary
Delivery Order | Institution Name | State | Institution Type | Website | Old Tech | Planned Work | Current Status | Phase | Launch Month | Start Date | End Date | % Complete | Primary Contact | Remarks
1 | Apeejay Institute Of Mass Communication | New Delhi | Higher Education | https://www.apeejay.edu/aimc/ | Joomla | WordPress | Live | Delivered | Nov 2025 | 2025-11-01 | 2025-11-30 | 100%
2 | ACFA Journal, Jalandhar | Haryana | Higher Education | https://journalsacfa.apeejay.edu/ | Joomla | WordPress | Live | Delivered | Jan 2026 | 2026-01-01 | 2026-01-31 | 100% |  | Complete New website created by ETS
3 | Apeejay Institute Of Design, Tuglakabad | New Delhi | Higher Education | https://www.apeejay.edu/aid/ | Joomla | WordPress | Live | Delivered | Jan 2026 | 2026-01-01 | 2026-01-31 | 100% |  | Done By ETS
4 | Apeejay School Of Management, Dwarka | New Delhi | Higher Education | https://www.apeejay.edu/asm/ | WordPress | WordPress version upgraded | Live | Delivered | Jan 2026 | 2026-01-01 | 2026-01-31 | 100% |  | Done By ETS
5 | Apeejay Stya University, Sohna | Haryana | Higher Education | https://university.apeejay.edu/ | WordPress | WordPress version upgraded | Live | Delivered | Jan 2026 | 2026-01-01 | 2026-01-31 | 100%
6 | Apeejay International School, Greater Noida | U.P. | School | https://www.apeejay.edu/intl/ | Joomla | WordPress | Live | Delivered | Feb 2026 | 2026-02-01 | 2026-02-28 | 100% |  | Website revamped by ETS
7 | Apeejay Rhythms Kinderworld, GK-2 | New Delhi | School | https://rhythms.apeejay.edu/ | WordPress | WordPress version upgraded | Live | Delivered | Feb 2026 | 2026-02-01 | 2026-02-28 | 100%
8 | Apeejay School Svran Global School, Faridabad (21D) | Haryana | School | https://apeejay.edu/asgs/ | Joomla | WordPress | Live | Delivered | Feb 2026 | 2026-02-01 | 2026-02-28 | 100% |  | Done By ETS
9 | Apeejay School, Faridabad | Haryana | School | https://apeejay.edu/faridabad/ | WordPress | WordPress version upgraded | Live | Delivered | Feb 2026 | 2026-02-01 | 2026-02-28 | 100%
10 | Apeejay School, Noida | U.P. | School | https://apeejay.edu/noida/ | WordPress | WordPress version upgraded | Live | Delivered | Feb 2026 | 2026-02-01 | 2026-02-28 | 100%
11 | Apeejay School, Sheikh Sarai | New Delhi | School | https://www.apeejay.edu/panchsheel/ | Joomla | Website revamp | WIP | In progress | Mar 2026 | 2026-03-01 | 2026-03-31 | 50% |  | In Process
12 | Apeejay School, Nerul | Navi Mumbai | School | https://www.apeejay.edu/nerul/ | Joomla | Website revamp | TBR | Revamp queue | Apr 2026 | 2026-04-01 | 2026-04-30 | 0%
13 | Apeejay School, Khargar | Navi Mumbai | School | https://www.apeejay.edu/kharghar/ | Joomla | Website revamp | TBR | Revamp queue | May 2026 | 2026-05-01 | 2026-05-31 | 0% |  | To be start
14 | Apeejay School, Mahavir Marg | Jalandhar | School | https://www.apeejay.edu/jalandhar/ | Joomla | Website revamp | TBR | Revamp queue | May 2026 | 2026-05-01 | 2026-05-31 | 0%
15 | Apeejay School, Rama Mandi, Hoshiarpur | Jalandhar | School | https://www.apeejay.edu/hoshiarpur/ | Joomla | Website revamp | TBR | Revamp queue | May 2026 | 2026-05-01 | 2026-05-31 | 0%
16 | Apeejay Rhythms, Model Town | Jalandhar | School | https://apeejay.edu/modeltown/ | WordPress | Version upgrade | TBR | Version upgrade queue | Jun 2026 | 2026-06-01 | 2026-06-30 | 0%
17 | Apeejay School, Model Town | Jalandhar | School | https://apeejay.edu/modeltown/ | WordPress | Version upgrade | TBR | Version upgrade queue | Jun 2026 | 2026-06-01 | 2026-06-30 | 0%
18 | Apeejay School, Tanda Road | Jalandhar | School | https://www.apeejay.edu/tandaroad/ | Joomla | Website revamp | TBR | Revamp queue | Jun 2026 | 2026-06-01 | 2026-06-30 | 0%
19 | Apeejay Shcool International, Panchsheel Park | New Delhi | School | https://intl.apeejay.edu/ | WordPress | Version upgrade | TBR | Version upgrade queue | Jul 2026 | 2026-07-01 | 2026-07-31 | 0%
20 | Apeejay Shcool, Pitampura | New Delhi | School | https://www.apeejay.edu/pitampura/ | Joomla | Website revamp | TBR | Revamp queue | Jul 2026 | 2026-07-01 | 2026-07-31 | 0%
21 | Apeejay School, Charkhi Dadri | Haryana | School | https://apeejay.edu/dadri/ | WordPress | Version upgrade | TBR | Version upgrade queue | Aug 2026 | 2026-08-01 | 2026-08-31 | 0%
22 | Apeejay School, Saket | New Delhi | School | https://www.apeejay.edu/saket/ | Joomla | Website revamp | TBR | Revamp queue | Aug 2026 | 2026-08-01 | 2026-08-31 | 0%
23 | Apeejay Institute Of Management & Engineering Technical Campus | Jalandhar | Higher Education | https://aimetc.apeejay.edu/ | WordPress | Version upgrade | TBR | Version upgrade queue | Sep 2026 | 2026-09-01 | 2026-09-30 | 0%
24 | Apeejay Sarasawti PG college of Girls, Charkhi Dadri, Bhiwani | Haryana | Higher Education | https://www.apeejay.edu/saraswati/ | Joomla | Website revamp | TBR | Revamp queue | Oct 2026 | 2026-10-01 | 2026-10-31 | 0%
25 | Apeejay College Of Fine Arts | Jalandhar | Higher Education | https://acfa.apeejay.edu/ | Joomla | Website revamp | TBR | Revamp queue | Dec 2026 | 2026-12-01 | 2026-12-31 | 0%
26 | Apeejay School Of Technology- School Of Architecture & Planning | Gr. Noida | Higher Education | https://www.apeejay.edu/architecture/ | Joomla | Website revamp | TBR | Revamp queue | Dec 2026 | 2026-12-01 | 2026-12-31 | 0%
27 | Bervin | New Delhi | Other | https://bervin.com | Joomla | Website revamp | TBR | Revamp queue | Jan 2027 | 2027-01-01 | 2027-01-31 | 0%
28 | Svran | New Delhi | Other | https://www.svran.com/ | Joomla | Website revamp | TBR | Revamp queue | Jan 2027 | 2027-01-01 | 2027-01-31 | 0%

## Gantt View
Gantt View
Visual delivery schedule by launch month. Bars represent the planned delivery month.
Back to Executive Summary |  | Open organized tracker
Order | Institution | Status | Work | Launch | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01
1 | Apeejay Institute Of Mass Communication | Live | WordPress | Nov 2025 | bar: 2025-11-01
2 | ACFA Journal, Jalandhar | Live | WordPress | Jan 2026 | bar: 2026-01-01
3 | Apeejay Institute Of Design, Tuglakabad | Live | WordPress | Jan 2026 | bar: 2026-01-01
4 | Apeejay School Of Management, Dwarka | Live | WordPress version upgraded | Jan 2026 | bar: 2026-01-01
5 | Apeejay Stya University, Sohna | Live | WordPress version upgraded | Jan 2026 | bar: 2026-01-01
6 | Apeejay International School, Greater Noida | Live | WordPress | Feb 2026 | bar: 2026-02-01
7 | Apeejay Rhythms Kinderworld, GK-2 | Live | WordPress version upgraded | Feb 2026 | bar: 2026-02-01
8 | Apeejay School Svran Global School, Faridabad (21D) | Live | WordPress | Feb 2026 | bar: 2026-02-01
9 | Apeejay School, Faridabad | Live | WordPress version upgraded | Feb 2026 | bar: 2026-02-01
10 | Apeejay School, Noida | Live | WordPress version upgraded | Feb 2026 | bar: 2026-02-01
11 | Apeejay School, Sheikh Sarai | WIP | Website revamp | Mar 2026 | bar: 2026-03-01
12 | Apeejay School, Nerul | TBR | Website revamp | Apr 2026 | bar: 2026-04-01
13 | Apeejay School, Khargar | TBR | Website revamp | May 2026 | bar: 2026-05-01
14 | Apeejay School, Mahavir Marg | TBR | Website revamp | May 2026 | bar: 2026-05-01
15 | Apeejay School, Rama Mandi, Hoshiarpur | TBR | Website revamp | May 2026 | bar: 2026-05-01
16 | Apeejay Rhythms, Model Town | TBR | Version upgrade | Jun 2026 | bar: 2026-06-01
17 | Apeejay School, Model Town | TBR | Version upgrade | Jun 2026 | bar: 2026-06-01
18 | Apeejay School, Tanda Road | TBR | Website revamp | Jun 2026 | bar: 2026-06-01
19 | Apeejay Shcool International, Panchsheel Park | TBR | Version upgrade | Jul 2026 | bar: 2026-07-01
20 | Apeejay Shcool, Pitampura | TBR | Website revamp | Jul 2026 | bar: 2026-07-01
21 | Apeejay School, Charkhi Dadri | TBR | Version upgrade | Aug 2026 | bar: 2026-08-01
22 | Apeejay School, Saket | TBR | Website revamp | Aug 2026 | bar: 2026-08-01
23 | Apeejay Institute Of Management & Engineering Technical Campus | TBR | Version upgrade | Sep 2026 | bar: 2026-09-01
24 | Apeejay Sarasawti PG college of Girls, Charkhi Dadri, Bhiwani | TBR | Website revamp | Oct 2026 | bar: 2026-10-01
25 | Apeejay College Of Fine Arts | TBR | Website revamp | Dec 2026 | bar: 2026-12-01
26 | Apeejay School Of Technology- School Of Architecture & Planning | TBR | Website revamp | Dec 2026 | bar: 2026-12-01
27 | Bervin | TBR | Website revamp | Jan 2027 | bar: 2027-01-01
28 | Svran | TBR | Website revamp | Jan 2027 | bar: 2027-01-01